## Sheet1
Date | Work Assigned | Work done | Remarks
week 1 | Setup SFML and project structure, added background graphics and basic scrolling — demo version of the game | completed
week 2 | Implemented Bird class: movement, animation, gravity, and input handling | completed
week 3 | Added pipe spawning system, land movement, and basic collision detection with pipes and ground | completed
week 4 | Built the game engine components (State Machine, Input Manager, Asset Manager, and Game loop) | completed
week 5 | Created Splash Screen and transitioned into Main Menu state | completed
week 6 | Designed Main Menu screen and integrated transition into Game State | completed
week 7 | Improved collision detection logic and tuned gameplay mechanics | completed
week 8 | Implemented scoring system and displayed real-time score | completed
week 9 | Design GameOver screen, score and high score | completed
week 10 | Started adding sound effects (flap, score, hit, and background music) | Completed